## Test plan
TEST PLAN
Introduction
Project: | ATM simulation - C console
Version: | 1.0.0
Resource: | 2 people
Create date: | 24/10/2026
Scope |  | Description | Note
In scope | - Card Insertion | Valid card, non-existent card, invalid format, expired card, locked card
| - Card Ejection | The card is returned when the session ends or when the card is locked
| - PIN Authentication | Correct PIN, incorrect PIN, exceeding the allowed number of attempts → card is locked
| - Navigation (main menu) | Display the menu, select valid and invalid options, return to the menu
| - Cash withdrawal | Valid amount, amount that is a multiple of the denomination, withdrawal limit, insufficient account balance, insufficient cash in the ATM cash dispenser. The account balance, ATM cash, and transaction records in the database are updated correctly
| - Balance Inquiry | The displayed balance matches the data in the database
Out of scope | - Transaction cancellation, Error handling |  | - Transaction cancellation done by Cash withdrawal
| - Cash deposit |  | - Cash deposit done by Cash withdrawal/Balance
| - Change PIN |  | - Change PIN done by PIN Authentication
- Transfer
| - Transaction history & receipt |  | - Receipt done by Transaction history
Purpose
Purpose | - Verify that the main ATM flow (insert card → enter PIN → menu → check balance / withdraw cash → return card) works according to the Sprint 1 requirements document. - Ensure that data in the database remains consistent after every transaction.
Approach |  | Note
Test levels | - Unit Test: | - Validate PIN/Card, State machine ATM
| - Integration Test: | - Read/Write card, account, transaction
| - Smoke Test: | - Quick check that the build is stable enough for further testing
| - System Test (black-box) | - End-to-end verification of the system against requirements
| - Regression Test | - Confirm that fixes and new changes do not break existing functionality
| - Acceptance / Demo | - Final walkthrough of the main flow for stakeholders
Test techniques | - Equivalence Partitioning
- Boundary Value Analysis
- Decision Table
- State Transition
- Error Guessing & Exploratory
- Config-change Test
Resource |  | Note
People: | 1 Tester, 1 Dev
Environment: | Windows 11
Tools: | Jira to log bug, Google Sheet to track test case
Schedule |  | Note
Day 1-2: | Read requirements, write test case
Day 3-4: | Complete test case, prepare data
Day 5-6: | Execute ->> test PIN Authentication, Balance Inquiry, Regression, log bug
Day 7-8: | Execute ->> test cash withdrawal + floe E2E, retesst bug fixed
Day 9: | Retest bug remain, exploratory
Day 10: | Regression, Bug report, Summary report
Entry Criteria & Exit Criteria
Entry Criteria | The requirements document is available and has been confirmed by the Dev as the version to be used for testing
The test environment is ready
Test cases for all features in the build have been written and reviewed by the Dev
Exit criteria | 100% test case have been executed
No open Critical/High bugs. Any remaining Medium/Low bugs have been confirmed by the Dev to be handled in the next sprint
The main flow passes at least 3 consecutive times, each run starting from a freshly reset database
The test summary report has been reviewed
Risk & Mitigation
Risk |  | Mitigation
Dev trễ build
Dữ liệu test lệch