## Timeline
ATM Machine - (V - Model)
Start: 14/09/2026 ¦ End: 08/01/2027 ¦ 17 weeks
| Phase | Tasks | Start day | End day | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
[5 empty] | 14/09 | 21/09 | 28/09 | 2026-05-10 | 2026-12-10 | 19/10 | 26/10 | 2026-02-11 | 2026-09-11 | 16/11 | 23/11 | 30/11 | 2026-07-12 | 14/12 | 21/12 | 28/12 | 2026-04-01
1 | Requirements & Analysis | Gather user's need | 14/09/2026 | 25/09/2026 | W2: MS 1: SRS Approved
System description (critical features) and System requirement analysis | bar: W1 to W2
2 | System design | Ramp-up testing | 28/09/2026 | 2026-09-10 | W3: Ramp-up-testing; W8: MS 2: Design Approved
|  | System / Architecture design | 2026-12-10 | 30/10/2026 | W5: System / Architecture design
|  | Test plan & Test strategy |  |  | W6: Test plan & Test strategy
|  | Module design |  |  | W6: Module design
|  | Test design |  |  | W6: Test design
3 | Coding/ Testing | Coding (C) & Review code | 2026-02-11 | 27/11/2026 | W9: Coding; W10: Review code; W11: Coding; W12: MS 3: Code Complete
|  | Test case |  |  | W9: Test case
|  | Fixing bug |  |  | W9: Fixing bug
4 | Testing and Acceptance Testing | Unit testing | 30/11/2026 | 2026-11-12 | W14: MS 4: Testing Complete
Integration | bar: W13 to W14
System testing | bar: W13 to W14